## List1
EUROSAI Portfolio Holders' Operational Planning Framework - Overview of the projects -
Name of the Portfolio: Strategic Goal 1
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties (lead SAI(s)) | Planned
|  |  |  | Results | Deadline
| Strategic Goal 1: | Supporting effective, innovative and relevant audits by promoting and brokering professional cooperation
1 | 1.1. To promote audit-related cooperation by acting as a broker between members | Parallel audit on Workforce 2030 - Challenges and Opportunities | SAI Israel | Joint Report | IVQ 2021
2 |  | Complete the International coordinated audit on prevention and consequences elimination of earthquakes | WGAFADC | Joint Report | Postponed
3 |  | Cooperative audit on plastic waste | WGEA | Kick of meeting took place in December 2019 Participating SAIs: Albania, Bulgaria, Hungary, Malta, Moldova, North Macedonia, Poland (coordinator), Portugal, Romania, Serbia, Slovakia, Turkey | Publication of the joint report planned for IVQ 2021
4 |  | Publish the EUROSAI TFMA Audit Compendium | TFMA | Audit Compendium No 2* published "Municipal Real Estate Management" | IIIQ 2021 (published)
5 |  | Cooperative audit “Municipalities’ Own Revenues for Providing Quality Services to the Citizens During Pandemic” | TFMA | Audit conducted | IIQ 2023
6 |  | Collecting and analysing information on the implementation of the United Nations Sustainable Development Goals in the municipalities of the TFMA countries | TFMA | Training session completed for project members Research completed | IIQ 2022
7 |  | Collecting and systematizing data on the manner/methods of monitoring the implementation of the recommendations given in the audit reports for local self-government units | TFMA | Report prepared | IIIQ 2021
8 | 1.2. To support the development of innovative audit approaches and methods making use of new technologies | BIEP (Benchmarking Information Exchange Project) | SAI Czech Republic | BIEP Portal offering ideas of topics to share data on and updating the information regularly | ongoing
9 |  | Project Group on Innovations in EUROSAI | SAI France | New format (t.b.d.) | ongoing
10 |  | Project Group on Investigations | SAI Netherlands | Seminar | postponed until it is possible to meet in person
11 |  | Raising the Awareness of the SAIs on the Enterprise Risk Management (ERM) of the auditees | SAI Turkey | t.b.d. | t.b.d.
12 |  | Auditing in the new normal: Connecting Technology to Audit Processess | SAI Turkey | Road map for the post-Covid era | IIQ 2022
13 | 1.3. To facilitate the sharing of knowledge and experience within EUROSAI and with external stakeholders and partners | EUROSAI Database on audits | SAI Czech Republic | Database updated regularly and working on improvements | ongoing
14 |  | EUROSAI Database on products | SAI Czech Republic | Database updated regularly and search filters improved | ongoing
15 |  | EUROSAI Database on surveys | SAI Czech Republic | Database updated regularly and working on improvements | ongoing
16 |  | Merging of EUROSAI Databases | SAI Czech Republic | Merging of EUROSAI databases into one in order for them to be more user-friendly and beneficial | IIQ2024
|  | Managing of Trainings | SAI Czech Republic | Managing of Traninings | PG Closed IVQ 2021 (PG Closed)
19 |  | Network for Ethics (both obj. 1.1. and 1.3.) | SAI Croatia and SAI Portugal | Knowledge sharing platform - to provide a permanent online collaboration platform for ethics related issues - e.g. promotion of theoretical and practical studies on SAIs’ ethics management, integrity awareness raising, and ethics related audit initiatives. Membership is open to all EUROSAI members. | ongoing
20 |  | Auditing the response to the COVID-19 pandemic | SAI UK | Lessons learned | ongoing
21 |  | Clubs of Expert | SAI Lithuania | Exchange of information on various topics via different formats | ongoing
22 |  | Travelling webinar | SAI Israel | Series of webinars on various topics | ongoing
23 |  | Create electronic information edition of the WG | WGAFADC | Electronic information edition | ongoing
24 |  | The CUBE | ITWG | Analytical online database of audit reports | ongoing
25 |  | Organize annual meetings and seminars on relevant topics on municipality audit once a year | TFMA | Annual meetings and seminars on municipality audit | ongoing
26 |  | Organize expert meetings on the basis of members' needs on municipaly audit | TFMA | Expert meetings | ongoing
27 |  | Manage the EUROSAI TFMA website | TFMA | Information shared on website | ongoing
28 |  | Manage EUROSAI TFMA social platforms | TFMA | Information shared on social platforms | ongoing
29 |  | Publish TFMA newsletters annually | TFMA | Annual newsletters | ongoing
30 |  | Facilitate communication between EUROSAI TFMA, EURORAI and NORPIA | TFMA | Sharing of knowledge and experience | ongoing
31 |  | Manage the emergency of the global COVID- 19 pandemic at local level of TFMA countries | TFMA | A special publication prepared | IVQ 2022
32 |  | Update database about the main municipal data/expenses annually | TFMA | Data updated | ongoing
Name of the Portfolio: Strategic Goal 2
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
| Strategic Goal 2: | Helping SAIs deal with new opportunities and challenges by supporting and facilitating their institutional development
| Overall SG2 | EUROSAI members capacity development needs analysis | SAI Poland and SAI Sweden | Identification of capacity development needs of European SAIs and public auditing in Europe | 2024
|  | EUROSAI Audit Methodology seminars | SAI Poland | Supporting SAIs in developing and improving their working methods, and to identify their potential needs. The 1st seminar were in Warsaw 2018 and a 2nd seminar is planned once in-person-meetings again are possible | 2024
|  | EUROSAI internship and secondment programme | SAI Poland | Initiated in 2019, the programme aim to help SAIs developing knowledge and skills of their staff | 2024
|  | New - Audit English | SAI Poland (Chair), SAI UK and SAI Sweden (co-chairs) - ToR in the process of approval | Aim to harmonise the English terminology related to public auditing and control - through linguistic training events | 2024
|  | New - Civil Society | Project Leader to be determined (tbd) - ToR tbd | Aim to explore SAIs cooperation with civil society and citizen engagement in the interest of enhanced SAIs’ impact and improved accountability. Project based on CBC framework on civil society, to collect good practices and exchange experience in the EUROSAI region | 2024
|  | New - Data envelopment Analysis (DEA) method | SAI Sweden - ToR tbd! | Aim to offer workshops to learn more about the DEA method, share experiences and gain practical knowledge. DEA is a quantitative method to empirically measure efficiency (best-practise) of decision-making units and a potential useful tool in performance audits | 2024
|  | Professional Training: 1. Research and Training Hub 2. The IT Audit Active Manual Workshop 3. The ITSA/ITASA Workshop | ITWG | IT Potential in SAIs enhanced and provision of assistance to SAIs in implementing guidelines | 2024
|  | Sharing knowledge and best practices via the CUBE - Control Space for e-Government Audit project | ITWG | IT potential in SAIs enhanced | 2024
|  | The accumulation of SAIs’ knowledge on issues of prevention and consequence elimination of disasters | WGAFADC | 1) Updated Glossary of Disaster-Related Terms 2) Updated knowledge base on the prevention and consequences elimination of disasters | 2024
| 2.2. To promote and encourage institutional development through self-assessments, peer reviews and other evaluations | New - SAI Evaluation tools and methods | SAI Sweden - ToR in the process of approval | Aim to help SAIs navigate among available tools to measure and assess their performance and operations (e.g. peer reviews, the SAI PMF, IntoSAINT, ITSA, ITASA and iCAT) | 2022
|  | IT Self-assessment (ITSA) | ITWG | Increased number of ITSA | 2024
|  | Rollout of ITSAs and ITASAs into other regions | ITWG | ITSA and ITASA promoted in other regions | 2024
|  | IT Audit Self-Assessment (ITASA) | ITWG | Increased number of ITASA | 2024
| 2.3. To promote and facilitate the implementation of INTOSAI’s Framework of Professional Pronouncements (IFPP) and contribute to its future development | Communication about the development of INTOSAI Professional Pronouncements | SAI Sweden | Increased knowledge of the INTOSAI Framework for Professional Pronouncement (IFPP) and strengthened ability among EUROSAI members to implement and apply IFPP. A workshop is planned for 2022 | 2024
|  | Translation of INTOSAI Professional Pronouncements into Russian | SAI Sweden, SAI Russia (provider of translation). EUROSAI Secretariat (web-coordinator) | The Professional Pronouncements translated into Russian | 2024
|  | Support IT related Standards and Guidelines | ITWG | EUROSAI contribution in IT related standards and guidelines | 2024
|  | Raising awareness of SAIs on the specifics of conducting audits on issues related to to the prevention and elimination of the consequences of various types of disasters | WGAFADC | Conducting seminars on the topics most relevant to the SAIs - members of the Working Group, identified on the basis of the survey and those that correspond to the field of activity of the Working Group | 2024
| 2.4. To follow and contribute to the development of INTOSAI initiatives and products for the professionalization of auditors | New - Cooperation with United Nations in relation to SDG audits | SAI Turkey - ToR tdb! | Cooperation with the United Nations in relation to SDG (Strategic Development Goals) audits – early stage of audit preparation, so that audits are best developed to assess the progress of SDGs implementation | 2024
|  | The follow-up of Sustainable Development Goals, in particular Goal 11 "Make cities inclusive, safe, resilient and sustainable" | WGAFADC | 1) Development of indicators for the follow-up of the SDGs in the area of prevention and consequences elimination of disasters 2) Report on EUROSAI members' efforts to implement the 2030 Agenda in the field of the WG’s activities | 2024
|  | New - Digital University of INTOSAI (U-INTOSAI) | SAI Russia - ToR tbd! | Promotion of U-INTOSAI – an educational platform available for all EUROSAI members to advance and improve SAI Capacity and the Professionalization of auditors. The resource usage includes publishing EUROSAI educational materials and benefiting from the available content as users | 2024
|  | Conduct audits on issues related to the prevention and elimination of the consequences of various types of disasters and create a database | WGAFADC | Сonduct coordinated audits and implement joint initiatives on issues related to the prevention and elimination of the consequences of various types of disasters. Create a database of matrices of audit issues in the field of disasters | 2024
| 2.5. Represent EUROSAI in the wider INTOSAI Community through appointment of specific liaisons | EUROSAI interaction and feedback towards main INTOSAI bodies (INTOSAI Secretariat, Congress, GB, IDI etc) | EUROSAI Presidency and Secretariat (SAI Spain) and EUROSAI leaders (on topical issues) | EUROSAI has an impact on INTOSAI global initiatives | 2024
|  | EUROSAI liason with INTOSAI Committees -PSC, KSC, CBC- and WG/TF | SG1 & SG2 co-leaders, SAI Sweden (PSC), SAI Poland (CBC), WG/TF and EUROSAI Presidency and Secretariat when needed
| Please note that: | * Projects written in black represent the activities of EUROSAI SG2 ongoing, green SG2 new projects... * Projects written in FAT letters represent the possible projects seeking for volunteer leader(s)/participant(s) and ToR tbd. TFEA-projects removed.
Name of the Portfolio: Overall Governance and Culture
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
1 | To review, revise and where necessary draft the main EUROSAI Regulations to reflect the enhancements of the governance, structure and modus operandi of EUROSAI foreseen in the ESP 2017-2023 | Project Group for Drafting a new EUROSAI Strategic Plan 2024 - 2030 | SAI Israel as the leader and SAI Czech Republic (Presidency), EUROSAI Secretariat (SAI Spain), SAIs Germany, Hungary, Latvia, Lithuania, Poland, Portugal, Sweden, Turkey, and United Kingdom | The PG aims at drafting a new EUROSAI Strategic Plan 2024 -2030 which shall be presented at the XII EUROSAI Congress | IIQ2022
|  | Project Group on EUROSAI Regulations | EUROSAI Secretariat (SAI Spain) as the leader and EUROSAI President (SAI Czech Republic), EUROSAI incoming President (SAI Israel), EUROSAI outgoing President (SAI Turkey), SAIs knowledgeable about INTOSAI/EUROSAI governance as participants | The PG aims to review and modify the following main EUROSAI Regulation; 1. EUROSAI Statutes. 2. EUROSAI Standard Procedures. 3. EUROSAI Financial Rules. 4. General Procedures to ESP | Permanent
2 | To contribute to the realisation of an effective, efficient and flexible organisational structure by promoting a culture of openness and debate and to facilitate the effective contribution of all GB members | Project on Creation of an enabling environment within GB to focus more on the strategic issues and facilitate the decision-making mechanism via regular and off-site meetings | CT members, EUROSAI Secretariat (SAI Spain) and Guests | Organisation of Governing Board meetings at the technical level to foster discussions on strategic and emerging issues. Organisation of the Coordination Team meetings before GB meetings to allow the agenda of the GB meetings to focus on strategic and substantial issues. Organisation of off-site meetings of EUROSAI GB Members when deemed necessary; otherwise conduct videoconferences at the presidential level | IIQ2024
3 | Taking into account the diversity of the region, to foster the inclusiveness of EUROSAI through reaching out to all members | Project on aiming at encouraging active membership and more participatory environment | EUROSAI Presidency (SAI Czech Republic) as leader and volunteer SAIs | Initiatives, questionnaires prepared, an assessment report drafted to reveal the barriers/challenges and propose the necessary actions for GB. Increased member participation and extension of the value of EUROSAI’s activities among its members and other stakeholders through enhanced communication and platforms. informal communication channels including social media. | IIQ2024
4 | To coordinate and monitor on a regular basis the execution of the EUROSAI Operational Plan | Regular monitoring and reviewing of the EUROSAI Operational Plan Functioning of a more simplified and effective reporting system which highlights the fundamental strategic issues and respective possible actions to be addressed. | CT members, EUROSAI Secretariat (SAI Spain) and SG co-leaders | Progress on the implementation of the Strategic Plan is followed closely. Overlap between different implementing bodies is minimised and synergies are maximised. EUROSAI is able to respond more quickly, effectively and with agility to new developments. | IIQ2022 IVQ2022
Name of the Portfolio: Communication
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
| Guiding principle 3. Promote increased member participation and extend the value of EUROSAI’s activities among its members and other stakeholders through enhanced communications; | Update of the EUROSAI Communcation Framework | GB/Congress | Draft updated EUROSAI Communication Framework put forward by the GB for XI Congress' approval. | IIQ2021
|  | Drafting of detailed guidelines for implementing an effective and enhanced communication in EUROSAI, in development of the updated Communication Framework (written procedures, tasks, roles and responsibilities, and frequency) | EUROSAI Secretariat (SAI Spain)/ Presidency/ PG on EUROSAI Regulations | Detailed guidelines to implement the Communication Framework, including the standardization of the main communication procedures within EUROSAI. It will include specific procedures, such as for the distribution and publicity of the results of the work carried out by the PGs, WGs and TFs to all EUROSAI members; information of the results of the Congress and the Governing Board's meetings or the response to journalists' queries. | IVQ2022
|  | Relaunch of the new EUROSAI website | PG for the Relaunch of the EUROSAI website Leader: EUROSAI Secretariat (SAI Spain) Participating SAIs: Israel, Czech Republic, UK, Estonia and Sweden | A revamped EUROSAI website already functional | IQ2023
|  | Review of the EUROSAI Magazine | EUROSAI Secretariat | A revised Magazine (content and format) in place | IQ2023
|  | EUROSAI Highlights Newsletter | SAI Israel | A regular newsletter condensing useful info for auditors regarding EUROSAI, using an attractive design (like a banner). For International Units to translate, if possible, into national languages. | IQ 2023
|  | EUROSAI Youtube channel | SAI Israel | YouTube channel, for promoting and disseminating EUROSAI activity | IV 2022
|  | Social media and other tools | Presidency / SAI Israel (in close consultation with the EUROSAI Secretariat) | Twitter -and any other social media if so decided- is used for regular communication (posting on the website's news). Exploring blogging sites, updating Wikipedia, etc | IVQ2022
|  | EUROSAI Welcome packages to new comers | EUROSAI Secretariat (SAI Spain)/ Presidency | Welcome packages (permanently revised and updated): - New Governing Board members (already available) - New EUROSAI Presidency (already available) Welcome package for new Heads of SAIs to be launched and updated | 2021-2024
|  | Promotion of EUROSAI within member SAIs - "Communication Package" | TBD | Package with presentations (EUROSAI at a glance, videos, PPTs, leaflet... of EUROSAI activities and outputs, mostly aimed for auditors (to be disseminated within the SAIs) | 2024
Name of the Portfolio: Emerging issues
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
1 | 1.3 Objective: To facilitate the sharing of knowledge and experience within EUROSAI and external stakeholders and Partners | To research and disseminate findings on future and emerging issues to EUROSAI members | SAI UK | Commission initial research on the audit environment and issues facing SAIs and audited bodies worldwide to include engagement with external stakeholders. Consult with members on emerging issues to identify which formal project groups support members needs. Communicate the results of future and emerging issues through a variety of channels (including formal reports, newsletters and seminars). Monitor the effectiveness of communication on emerging issues. | IQ2022 IQ2022 Ongoing Ongoing Annually
2 |  | Raise awareness of EUROSAI members of audit methodological issues that will help audited bodies increase insight and efficiency | SAI UK and SAI Lithuania/Germany | A rolling programme of seminars on developing issues for example, data analytics and use of AI in auditing. To be held on a frequency of two per year and will deep dive into specific subjects to compare how SAIs are addressing them to identify best practice and common approaches. A report of the findings will be produced at the end of each seminar. | Ongoing
3 |  | Continued cooperation with INTOSAI Supervisory Committee on Emerging Issues | EUROSAI Secretariat and SAI UK | Working with the Secretariat build strong working relations with the INTOSAI Supervisory Committee on Emerging Issues and communicate with EUROSAI members on the resulting issues. | Ongoing
4 |  | Help support the sharing of knowledge of emerging issues in a timely way | SAI UK | Close cooperation with SG2 lead to help ensure that emerging issues are communicated to EUROSAI members at the right time to be useful. Using different and appropriate channels to share information and benchmark approaches, making the most of formal and informal communication channels including social media. | Ongoing
5 |  | Support project groups to effectively meet their objectives and help manage the closedown when no longer needed | SAI UK and SAI Czech Republic | Support the COVID-19 Project Group in its second year of operation to streamline the workstreams and make sure that it covers the themes that remain relevant. Produce second annual report by June 2022. Support the Risks and Climate Crisis Project Group in developing active workstreams that meet the needs of member on developing environmental issues. The project group will aim to meet no less than three times per year and an update of work will be provided via the EUROSAI newsletter after each meeting. Formal report of the group at the end of 2022. | IIQ2022 IVQ2022
6 |  | Communicate issues identified by external stakeholders that are relevant to SAIs strategic planning | SAI Latvia and SAI UK | Work closely with the Portfolio holders that manage EUROSAI relationships with external bodies to make good use of all sources of information and knowledge that can help identify emerging issues that EUROSAI should focus upon. | Ongoing
Name of the Portfolio: Relations with non-SAI stakeholders
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
1 | 1.2. To support the development of innovative audit approaches and methods making use of new technologies | International-level network development: Focus on solidification of professional cooperation and knowledge sharing with relevant organizations internationally; | SAI Latvia | 1.1. On-going identification of opportunities to organize EUROSAI input in international events or cooperation with relevant organizations | 2021-2024
|  |  |  | 1.1.1. Established plan with ECIIA on continued cooperation established under SAI Belgium and SAI Netherlands | I Q 2022
| 1.3. To facilitate the sharing of knowledge and experience within EUROSAI and with external stakeholders and partners |  |  | 1.2. In cooperation with EUROSAI members, events to showcase experience prepares and organized | 2021-2024
|  |  |  | 1.2.1.EUROSAI/ECA side-event 'Translating climate ambition into delivery' at the UNCCC COP26 organized | IV Q 2021
|  |  |  | 1.2.2. Joint EUROSAI-ECIIA Forum (theme TBD) | III Q 2022
2 | 1.3. To facilitate the sharing of knowledge and experience within EUROSAI and with external stakeholders and partners | Capacity building on non-SAI stakeholder engagement: Build upon national-level experiences with non-SAI stakeholders to strengthen value for citizens. | SAI Latvia | 2.1. Survey among EUROSAI members on experiences in working with NGOs and other organizations on the national level | II Q 2022
|  |  |  | 2.2. Extraction and analysis of survey results to identify best practices in working with NGOs and other organizations on the national level | IV Q 2022
|  |  |  | 2.3. Exchange of best practises applied by EUROSAI members (format TBD) | III Q 2023
Name of the Portfolio: Relations with INTOSAI Regional Organisations
No. | Objective(s) (of the Strategic Plan relating to the project) | Project (title of the project) | Responsible parties | Planned
|  |  |  | Results | Deadline
1 | Guiding principles; 4 & 5 principle 4: Identify, represent and advocate its members'views and interests o subjects under development in INTOSAI principle 5: Enhance cooperation with INTOSAI Regional Organizations | Support the EUROSAI Governing Board/Congress in promoting an enhanced cooperation with the INTOSAI and its Regional Organizations, by formulating proposals in line with SGs and ensuring approriate representation in INTOSAI of EUROSAI interests | EUROSAI Secretariat (Spain) /Coordination Team/EUROSAI representatives in the INTOSAI GB | GB and Congress are informed and received adequate proposals by the Secretariat (in close consultation with the CT) concerning such cooperation. EUROSAI GB receives timely information from the regional representatives in the INTOSAI GB and is consulted on key matters that may affect the Organisation. | Permanent
2 |  | Foster dialogue with all Regional Organizations in INTOSAI fora meetings to identify areas and topics of mutual interest | EUROSAI Secretariat (Spain) & key players in EUROSAI (mostly SGs co-leaders) | Promote the inclusion of a region-to-region practical knowledge sharing session in the agenda of the INTOSAI-Regions Coordination Platform. | IQ 2018
|  |  |  | Secretariat ran and coordinated the first session (Oslo, 2018) and contributed to the second chaired by OLACEFS (Cape Town, 2019). Discussions held and results/info shared with EUROSAI counterparts. No meeting was held in 2020 due to the pandemic | 2018-2020
|  |  |  | Meetings would be held on needs basis as decided in 2021. Best practices/leasons learned are shared mostly within the Round table of Regions (mostly in remote format and in-person when possible). | 2021-2024
3 |  | Coordinate knowledge sharing and cooperation activities on topics of mutual interest between bodies and actors of EUROSAI and their peers in the other INTOSAI Regional Organizations | EUROSAI Secretariat (SAI Spain) & key players in EUROSAI | Effective cooperation, links established/ conections made and fully working. Exchanges of information, materials, lists, dbs etc. facilitated. Cooperation in webinars/events facilitating experts put in practice. | Permanent
4 |  | To support the organization of joint events with added value for participants, according to ToR approved by the GB and agreed with ASOSAI, OLACEFS and ARABOSAI | EUROSAI Secretariat (SAI Spain) | ToRs for the organisation of Joint Events signed with OLACEFS, ASOSAI and ARABOSAI | IVQ 2018
|  |  |  | Joint Conferences with ASOSAI (Jerusalem) and OLACEFS (e-format hosted by SAI of Hungary) following the ToRs | 2019 (JC ASOSAI) & 2020 (JC OLACEFS)
|  |  |  | VI EUROSAI- ARABOSAI Joint Conference (in Kyiv) held following the ToR | IIQ2022
5 |  | To launch practical cooperation with AFROSAI following the framework agreed with AFROSAI´s counterparts | EUROSAI Secretariat (SAI Spain) | EUROSAI-AFROSAI framework in place | IVQ 2018
6 |  |  | EUROSAI Secretariat (SAI Spain) & key players in EUROSAI | Practical cooperation carried out: a) mutual exchange of list of training events; b) EUROSAI experts supporting the AFROSAI Seminar hel on QC&QA in El Cairo (June 2019) c)1st EUROSAI-AFROSAI Joint Seminar on SDGs held in Lisbon (November 2019); d)financial scheme for EUROSAI and AFROSAI activitites approved by both Regions | 2019
|  |  |  | Practical cooperation developed as described in the framework | 2021-2024
Activities already carried out
Overall Governance and Culture
Strategic Goal 1
Strategic Goal 2
Communication
Emerging issues
Relations with non-SAI stakeholders
Relations with INTOSAI Regional Organisations
Note on D29: RUCKÝ Jaroslav: According to the description these two PGs are overlapping. We sugest merging them and have two co-leaders? Or please differentiate these two PGs.